## Sprint 2
Task # | Module Name | RCT ID | Core Feature | Task Description | Tracking (Y/N) | Start Date | End Date | % Progress | Task Owner
1 | Match & Book Rides | O2.02 | Filter Vehicles | Search for Proper UI Design for Vehicle Filtering | N | 2025-03-26 | 2025-03-27 | 100% | Manas Karande
2 | Match & Book Rides | O2.02 | Filter Vehicles | Implement Filter Logic for Vehicle Search | Y | 2025-03-27 | 2025-03-28 | 100% | Karan Yadav
3 | Match & Book Rides | O2.02 | Filter Vehicles | Validate Filter Options and Results for Accuracy | N | 2025-03-28 | 2025-03-30 | 100% | Abhyaung Havale
4 | Match & Book Rides | O2.02 | Filter Vehicles | Perform Exploratory Testing on Filter Functionality | N | 2025-03-30 | 2025-03-31 | 100% | Himanshu Garg
5 | Match & Book Rides | O2.03 | Apply Promo Code | Search for Proper UI Design for Applying Promo Codes | N | 2025-03-26 | 2025-03-27 | 100% | Anish Ayare
6 | Match & Book Rides | O2.03 | Apply Promo Code | Implement Promo Code Application Logic | Y | 2025-03-27 | 2025-03-29 | 100% | Abhay Soni
7 | Match & Book Rides | O2.03 | Apply Promo Code | Validate Promo Code Application Process for Accuracy | N | 2025-03-29 | 2025-03-30 | 100% | Shivam Dubey
8 | Match & Book Rides | O2.03 | Apply Promo Code | Perform Exploratory Testing on Promo Code Functionality | N | 2025-03-30 | 2025-03-31 | 100% | Shivani Jain
9 | Match & Book Rides | O2.04 | Book Vehicles | Search for Proper UI Design for Booking a Ride | N | 2025-04-01 | 2025-04-02 | 100% | Abhishek Kasula
10 | Match & Book Rides | O2.04 | Book Vehicles | Implement Booking Logic for Ride Booking | Y | 2025-04-02 | 2025-04-04 | 100% | Manas Karande
11 | Match & Book Rides | O2.04 | Book Vehicles | Validate Booking Process for Accuracy | N | 2025-04-05 | 2025-04-06 | 100% | Manjusha Domala
12 | Match & Book Rides | O2.04 | Book Vehicles | Perform Exploratory Testing on Booking Functionality | N | 2025-04-07 | 2025-04-08 | 100% | Himanshu Garg
13 | Match & Book Rides | O2.05 | Manage Bookings | Search for Proper UI Design for Managing Bookings | N | 2025-04-01 | 2025-04-02 | 100% | Abhyaung Havale
14 | Match & Book Rides | O2.05 | Manage Bookings | Implement Booking Management Logic | Y | 2025-04-03 | 2025-04-05 | 100% | Karan Yadav
15 | Match & Book Rides | O2.05 | Manage Bookings | Validate Booking Management Process for Accuracy | N | 2025-04-06 | 2025-04-07 | 100% | Anish Ayare
16 | Match & Book Rides | O2.05 | Manage Bookings | Perform Exploratory Testing on Booking Management Functionality | N | 2025-04-09 | 2025-04-11 | 100% | Abhay Soni
17 | Process Payments | O3.01 | Process Payment | Search for Proper UI Design for Payment Processing | N | 2025-04-07 | 2025-04-08 | 100% | Manas Karande
18 | Process Payments | O3.01 | Process Payment | Implement API for Payment Gateway Integration | Y | 2025-04-09 | 2025-04-11 | 100% | Himanshu Garg
19 | Process Payments | O3.01 | Process Payment | Implement Validation Fields to Ensure Accurate Payment Details | N | 2025-04-12 | 2025-04-13 | 100% | Abhyaung Havale
20 | Process Payments | O3.01 | Process Payment | Perform Exploratory Testing on Payment Processing Functionality | N | 2025-04-13 | 2025-04-14 | 90% | Karan Yadav
21 | Process Payments | O3.02 | Secure Payment | Search for Proper UI Design for Secure Payment Interface | N | 2025-04-07 | 2025-04-08 | 100% | Anish Ayare
22 | Process Payments | O3.02 | Secure Payment | Implement Encryption for Secure Payment Transactions | Y | 2025-04-09 | 2025-04-11 | 100% | Abhay Soni
23 | Process Payments | O3.02 | Secure Payment | Validate Secure Payment Fields to Ensure Compliance with Standards | N | 2025-04-12 | 2025-04-13 | 100% | Shivam Dubey
24 | Process Payments | O3.02 | Secure Payment | Perform Security Testing on Secure Payment Functionality | N | 2025-04-13 | 2025-04-14 | 100% | Shivani Jain
Task # | Module Name
1 | Match & Book Rides
2 | Match & Book Rides
3 | Match & Book Rides
4 | Match & Book Rides
5 | Match & Book Rides
6 | Match & Book Rides
7 | Match & Book Rides
8 | Match & Book Rides
9 | Match & Book Rides
10 | Match & Book Rides
11 | Match & Book Rides
12 | Match & Book Rides
13 | Match & Book Rides
14 | Match & Book Rides
15 | Match & Book Rides
16 | Match & Book Rides
17 | Match & Book Rides
18 | Match & Book Rides
19 | Match & Book Rides
20 | Match & Book Rides
21 | Match & Book Rides
22 | Match & Book Rides
23 | Match & Book Rides
24 | Match & Book Rides
25 | Match & Book Rides
26 | Match & Book Rides
27 | Match & Book Rides
28 | Match & Book Rides
29 | Match & Book Rides
30 | Match & Book Rides
31 | Match & Book Rides
32 | Match & Book Rides
33 | Process Payments
34 | Process Payments
35 | Process Payments
36 | Process Payments
37 | Process Payments
38 | Process Payments
39 | Process Payments
40 | Process Payments
41 | Execute and Track Rides
42 | Execute and Track Rides
43 | Execute and Track Rides
44 | Execute and Track Rides
45 | Execute and Track Rides
46 | Execute and Track Rides
47 | Execute and Track Rides
48 | Execute and Track Rides
49 | Execute and Track Rides
50 | Execute and Track Rides
51 | Execute and Track Rides
52 | Execute and Track Rides
53 | Collect Feedback, Support & Marketing
54 | Collect Feedback, Support & Marketing
55 | Collect Feedback, Support & Marketing
56 | Collect Feedback, Support & Marketing
57 | Collect Feedback, Support & Marketing
58 | Collect Feedback, Support & Marketing
59 | Collect Feedback, Support & Marketing
60 | Collect Feedback, Support & Marketing
61 | Collect Feedback, Support & Marketing
62 | Collect Feedback, Support & Marketing
63 | Collect Feedback, Support & Marketing
64 | Collect Feedback, Support & Marketing
65 | Collect Feedback, Support & Marketing
66 | Collect Feedback, Support & Marketing
67 | Collect Feedback, Support & Marketing
68 | Collect Feedback, Support & Marketing

## Sprint 3
Task # | Module Name | RCT ID | Core Feature | Task Description | Tracking (Y/N) | Start Date | End Date | % Progress | Task Owner
1 | Process Payments | O3.03 | View Payment History | Search for Proper UI Design for Viewing Payment History | N | 2025-04-16 | 2025-04-17 | 100% | Shivam Dubey
2 | Process Payments | O3.03 | View Payment History | Implement Logic to Fetch and Display Payment History | Y | 2025-04-18 | 2025-04-20 | 100% | Shivani Jain
2 | Process Payments | O3.03 | View Payment History | Produce Test Design Specification | N | 2025-04-21 | 2025-04-22 | 50% | Manas Karande
3 | Process Payments | O3.03 | View Payment History | Produce Test Case Specification | N | 2025-04-21 | 2025-04-22 | 50% | Abhay Soni
4 | Process Payments | O3.03 | View Payment History | Validate Payment History Display for Accuracy | N | 2025-04-21 | 2025-04-22 | 100% | Abhishek Kasula
5 | Process Payments | O3.03 | View Payment History | Perform Testing on View Payment History Functionality | N | 2025-04-23 | 2025-04-24 | 0% | Manjusha Domala
6 | Execute and Track Rides | O4.01 | View Bookings | Search for Proper UI Design for Viewing Ride History | N | 2025-04-16 | 2025-04-17 | 100% | Abhishek Kasula
7 | Execute and Track Rides | O4.01 | View Bookings | Implement API to Fetch and Display Ride History | Y | 2025-04-18 | 2025-04-20 | 100% | Manjusha Domala
8 | Execute and Track Rides | O4.01 | View Bookings | Produce Test Design Specification | N | 2025-04-21 | 2025-04-22 | 50% | Karan Yadav
9 | Execute and Track Rides | O4.01 | View Bookings | Produce Test Case Specification | N | 2025-04-21 | 2025-04-22 | 50% | Shivam Dubey
10 | Execute and Track Rides | O4.01 | View Bookings | Validate Ride History Data for Accuracy | N | 2025-04-21 | 2025-04-22 | 100% | Manas Karande
11 | Execute and Track Rides | O4.01 | View Bookings | Perform Testing on Ride History Functionality | N | 2025-04-23 | 2025-04-24 | 0% | Himanshu Garg
12 | Execute and Track Rides | O4.02 | GPS Tracking | Search for Proper UI Design for GPS Tracking Interface | N | 2025-04-19 | 2025-04-20 | 100% | Shivam Dubey
13 | Execute and Track Rides | O4.02 | GPS Tracking | Implement GPS Tracking API for Real-Time Location Updates | Y | 2025-04-21 | 2025-04-23 | 100% | Shivani Jain
14 | Execute and Track Rides | O4.02 | GPS Tracking | Produce Test Design Specification | N | 2025-04-22 | 2025-04-24 | 20% | Abhay Soni
15 | Execute and Track Rides | O4.02 | GPS Tracking | Produce Test Case Specification | N | 2025-04-22 | 2025-04-24 | 20% | Anish Ayare
16 | Execute and Track Rides | O4.02 | GPS Tracking | Validate GPS Tracking Data for Accuracy | N | 2025-04-24 | 2025-04-25 | 0% | Abhishek Kasula
17 | Execute and Track Rides | O4.02 | GPS Tracking | Perform Testing on GPS Tracking Functionality | N | 2025-04-25 | 2025-04-26 | 0% | Manjusha Domala
18 | Execute and Track Rides | O4.03 | Route Optimizing | Search for Proper UI Design for Route Optimization Interface | N | 2025-04-19 | 2025-04-20 | 100% | Manas Karande
19 | Execute and Track Rides | O4.03 | Route Optimizing | Implement Route Optimization Algorithm for Efficient Paths | Y | 2025-04-21 | 2025-04-23 | 100% | Himanshu Garg
20 | Execute and Track Rides | O4.03 | Route Optimizing | Produce Test Design Specification | N | 2025-04-22 | 2025-04-24 | 70% | Shivam Dubey
21 | Execute and Track Rides | O4.03 | Route Optimizing | Produce Test Case Specification | N | 2025-04-22 | 2025-04-24 | 30% | Shivani Jain
22 | Execute and Track Rides | O4.03 | Route Optimizing | Validate Route Optimization Results for Efficiency | N | 2025-04-24 | 2025-04-25 | 0% | Abhyaung Havale
23 | Execute and Track Rides | O4.03 | Route Optimizing | Perform Testing on Route Optimization Functionality | N | 2025-04-25 | 2025-04-26 | 0% | Karan Yadav
24 | Collect Feedback, Support & Marketing | O5.01 | Collect Feedback | Search for Proper UI Design for Collecting Feedback | N | 2025-04-16 | 2025-04-17 | 100% | Manas Karande
25 | Collect Feedback, Support & Marketing | O5.01 | Collect Feedback | Implement Logic to Collect and Store Feedback | Y | 2025-04-18 | 2025-04-20 | 100% | Himanshu Garg
26 | Collect Feedback, Support & Marketing | O5.01 | Collect Feedback | Produce Test Design Specification | N | 2025-04-20 | 2025-04-21 | 100% | Anish Ayare
27 | Collect Feedback, Support & Marketing | O5.01 | Collect Feedback | Produce Test Case Specification | N | 2025-04-20 | 2025-04-21 | 100% | Himanshu Garg
28 | Collect Feedback, Support & Marketing | O5.01 | Collect Feedback | Validate Feedback Collection Process for Accuracy | N | 2025-04-21 | 2025-04-22 | 100% | Abhyaung Havale
29 | Collect Feedback, Support & Marketing | O5.01 | Collect Feedback | Perform Testing on Feedback Collection Functionality | N | 2025-04-23 | 2025-04-24 | 0% | Karan Yadav
30 | Collect Feedback, Support & Marketing | O5.02 | Issue Resolution | Search for Proper UI Design for Issue Resolution Interface | N | 2025-04-25 | 2025-04-26 | 0% | Abhishek Kasula
31 | Collect Feedback, Support & Marketing | O5.02 | Issue Resolution | Implement Backend Logic for Issue Reporting and Resolution | Y | 2025-04-27 | 2025-04-29 | 0% | Manjusha Domala
32 | Collect Feedback, Support & Marketing | O5.02 | Issue Resolution | Produce Test Design Specification | N | 2025-04-28 | 2025-04-30 | 0% | Abhishek Kasula
33 | Collect Feedback, Support & Marketing | O5.02 | Issue Resolution | Produce Test Case Specification | N | 2025-04-28 | 2025-04-30 | 0% | Shivam Dubey
34 | Collect Feedback, Support & Marketing | O5.02 | Issue Resolution | Validate Issue Resolution Process for Accuracy | N | 2025-04-30 | 2025-04-01 | 0% | Manas Karande
35 | Collect Feedback, Support & Marketing | O5.02 | Issue Resolution | Perform Testing on Issue Resolution Functionality | N | 2025-05-02 | 2025-05-03 | 0% | Himanshu Garg
36 | Collect Feedback, Support & Marketing | O5.03 | Marketing and Advertising | Search for Proper UI Design for Promotional Activities Interface | N | 2025-04-25 | 2025-04-26 | 0% | Shivam Dubey
37 | Collect Feedback, Support & Marketing | O5.03 | Marketing and Advertising | Implement Backend Logic for Managing Promotional Campaigns | Y | 2025-04-27 | 2025-04-29 | 0% | Shivani Jain
38 | Collect Feedback, Support & Marketing | O5.03 | Marketing and Advertising | Produce Test Design Specification | N | 2025-04-28 | 2025-04-30 | 0% | Manjusha Domala
39 | Collect Feedback, Support & Marketing | O5.03 | Marketing and Advertising | Produce Test Case Specification | N | 2025-04-28 | 2025-04-30 | 0% | Abhay Soni
40 | Collect Feedback, Support & Marketing | O5.03 | Marketing and Advertising | Validate Promotional Campaigns for Accuracy and Effectiveness | N | 2025-04-30 | 2025-04-01 | 0% | Abhishek Kasula
41 | Collect Feedback, Support & Marketing | O5.03 | Marketing and Advertising | Perform Testing on Promotional Activities Functionality | N | 2025-05-02 | 2025-05-03 | 0% | Manjusha Domala
42 | Collect Feedback, Support & Marketing | O5.04 | Send Promotional Notification | Search for Proper UI Design for Notification System | N | 2025-04-25 | 2025-04-26 | 0% | Abhyaung Havale
43 | Collect Feedback, Support & Marketing | O5.04 | Send Promotional Notification | Implement Notification System for Sending Alerts (e.g., Email/Push) | Y | 2025-04-27 | 2025-04-29 | 0% | Karan Yadav
44 | Collect Feedback, Support & Marketing | O5.04 | Send Promotional Notification | Produce Test Design Specification | N | 2025-04-28 | 2025-04-30 | 0% | Shivam Dubey
45 | Collect Feedback, Support & Marketing | O5.04 | Send Promotional Notification | Produce Test Case Specification | N | 2025-04-28 | 2025-04-30 | 0% | Manas Karande
46 | Collect Feedback, Support & Marketing | O5.04 | Send Promotional Notification | Validate Notification Delivery for Reliability | N | 2025-04-30 | 2025-04-01 | 0% | Anish Ayare
47 | Collect Feedback, Support & Marketing | O5.04 | Send Promotional Notification | Perform Testing on Notification Functionality | N | 2025-05-02 | 2025-05-03 | 0% | Abhay Soni
Task # | Module Name
1 | Match & Book Rides
2 | Match & Book Rides
3 | Match & Book Rides
4 | Match & Book Rides
5 | Match & Book Rides
6 | Match & Book Rides
7 | Match & Book Rides
8 | Match & Book Rides
9 | Match & Book Rides
10 | Match & Book Rides
11 | Match & Book Rides
12 | Match & Book Rides
13 | Match & Book Rides
14 | Match & Book Rides
15 | Match & Book Rides
16 | Match & Book Rides
17 | Match & Book Rides
18 | Match & Book Rides
19 | Match & Book Rides
20 | Match & Book Rides
21 | Match & Book Rides
22 | Match & Book Rides
23 | Match & Book Rides
24 | Match & Book Rides
25 | Match & Book Rides
26 | Match & Book Rides
27 | Match & Book Rides
28 | Match & Book Rides
29 | Match & Book Rides
30 | Match & Book Rides
31 | Match & Book Rides
32 | Match & Book Rides
33 | Process Payments
34 | Process Payments
35 | Process Payments
36 | Process Payments
37 | Process Payments
38 | Process Payments
39 | Process Payments
40 | Process Payments
41 | Execute and Track Rides
42 | Execute and Track Rides
43 | Execute and Track Rides
44 | Execute and Track Rides
45 | Execute and Track Rides
46 | Execute and Track Rides
47 | Execute and Track Rides
48 | Execute and Track Rides
49 | Execute and Track Rides
50 | Execute and Track Rides
51 | Execute and Track Rides
52 | Execute and Track Rides
53 | Collect Feedback, Support & Marketing
54 | Collect Feedback, Support & Marketing
55 | Collect Feedback, Support & Marketing
56 | Collect Feedback, Support & Marketing
57 | Collect Feedback, Support & Marketing
58 | Collect Feedback, Support & Marketing
59 | Collect Feedback, Support & Marketing
60 | Collect Feedback, Support & Marketing
61 | Collect Feedback, Support & Marketing
62 | Collect Feedback, Support & Marketing
63 | Collect Feedback, Support & Marketing
64 | Collect Feedback, Support & Marketing
65 | Collect Feedback, Support & Marketing
66 | Collect Feedback, Support & Marketing
67 | Collect Feedback, Support & Marketing
68 | Collect Feedback, Support & Marketing