## Road Map
RideEase
|  |  | SPRINT 1 | SPRINT 2 | SPRINT 3
Application Modules | Feature Backlog | Story Points | SPRINT1 - 03/25/2025 | SPRINT2 - 04/15/2025 | SPRINT3 - 05/06/2025
01. Profile Management | 01.01 Create Account | 3 | X
| 01.02 Modify Account | 3 | X
| 01.03 View Account Summary | 4 | X
| 01.03 Assign Roles | 2 | X
| 01.05 Access Customer Support | 2 | X
02. Match & book Rides | 02.01 Search Vehicles | 2 | X
| 02.02 Filter Vehicles | 4 |  | X
| 02.03 Apply Promo codes | 2 |  | X
| 02.04 Book Vehicles | 3 |  | X
| 02.05 Manage Bookings | 3 |  | X
03.Process Payments | 03.01 Process Payments | 3 |  | X
| 03.02 Secure Payment | 2 |  | X
| 03.03 View Payment History | 3 |  |  | X
04. Execute & Track Rides | 04.01 View Bookings | 5 |  |  | X
| 04.02 GPS Tracking | 4 |  |  | X
| 04.03 Route Optimizing | 4 |  |  | X
04.04 Driver Communication
05. Collect Feedback, Support & Marketing | 05.01 Collect Feedback | 2 |  |  | X
| 05.02 Issue Resolution | 2 |  |  | X
| 05.03 Marketing and advertisements | 2 |  |  | X
| 05.04 Send Promotional Notifications | 2 |  |  | X
|  | VELOCITY: | 16 | 17 | 24

## Jira Road Map S1
Timeline/Roadmap View: Months
Timeline/Roadmap View: Weeks
Kanban Board

## Jira Road Map S2
Timeline/Roadmap View: Months
Timeline/Roadmap View: Weeks
Kanban Board

## Jira Road Map S3
Timeline/Roadmap View: Months
Timeline/Roadmap View: Weeks
Kanban Board